## 0 · README
PICK1 · MASTER TRACKER
How to use this
This sheet is the EXECUTION log. The strategy doc (launch/MASTER_STRATEGY.md) is the plan; this is the daily-update tracker.
Update cadence: every night before bed. Takes ~3 min.
Sundays: full audit + reallocation decisions for the week ahead.
The 7 tabs
1. KPI Dashboard — top-level daily numbers (signups, CPL, etc.)
2. Content Calendar — every post planned + posted, with perf
3. Ad Performance — Meta + TikTok Spark per-day per-ad
4. Channel ROI — which channel is winning, % of total
5. Activations — the 5 viral activations + state
6. Influencer Outreach — the 20-DM micro-trade program
7. Pick Performance — daily pick record (the receipts wall)
North Star
1,500 waitlist signups by May 31. Stretch target: 2,500.
Budget: $1,000 total. CPL target: < $1.50.
Quick references
Strategy doc: launch/MASTER_STRATEGY.md
Site: https://pick1.live
FB Page: https://www.facebook.com/profile.php?id=61589631453496
Resend domain: pick1.live (verified)
Supabase proj: lgnjawngkiamlngcffrk (eu-central-2)

## 1 · KPI Dashboard
PICK1 · DAILY KPI DASHBOARD (May 13 → May 31)
North Star: 1,500 waitlist signups by May 31 · Budget: $1,000
Day | Date | Signups (cumulative) | Signups (today) | Meta $ today | Meta signups today | Meta CPL | Organic signups today | IG followers | TikTok followers | Email open % | Referral shares | Notes
Day 1 | 2026-05-13 | 1 | 1
Day 2 | 2026-05-14
Day 3 | 2026-05-15
Day 4 | 2026-05-16
Day 5 | 2026-05-17
Day 6 | 2026-05-18
Day 7 | 2026-05-19
Day 8 | 2026-05-20
Day 9 | 2026-05-21
Day 10 | 2026-05-22
Day 11 | 2026-05-23
Day 12 | 2026-05-24
Day 13 | 2026-05-25
Day 14 | 2026-05-26
Day 15 | 2026-05-27
Day 16 | 2026-05-28
Day 17 | 2026-05-29
Day 18 | 2026-05-30
Day 19 | 2026-05-31

## 2 · Content Calendar
CONTENT CALENDAR — every post across every channel
Date | Channel | Format | Pillar | Topic / Hook | Status | URL | Views | Likes | Shares | Signups attributed
2026-05-13 | TikTok | Reel | Receipt | Yesterday 2-1 (SAS 126-97 lock) | Drafted |  | 0 | 0 | 0 | 0
2026-05-13 | TikTok | Reel | Daily Pick | Tonight's lock: MCI 81.2% confidence | Drafted |  | 0 | 0 | 0 | 0
2026-05-13 | IG | Static | Receipt | Post #2: SAS 126-97 bold static | To render |  | 0 | 0 | 0 | 0
2026-05-13 | IG | Story | Daily Pick | Pick locked 🔒 (link sticker) | Drafted |  | 0 | 0 | 0 | 0
2026-05-13 | Twitter | Tweet | Receipt | Yesterday: SAS 126-97 + tonight tease | Drafted |  | 0 | 0 | 0 | 0
2026-05-13 | Twitter | Tweet | Daily Pick | 3pm: MCI lock reveal | Scheduled |  | 0 | 0 | 0 | 0
2026-05-13 | Reddit | Comment | Receipt | r/sportsbook daily-talk thread | Drafted |  | 0 | 0 | 0 | 0
2026-05-13 | Meta | Static Ad | Receipt | Ad 1: 'Yesterday: Spurs 126-97 ✓' | To render |  | 0 | 0 | 0 | 0
2026-05-13 | Meta | Static Ad | Daily Pick | Ad 2: 'Tonight's lock 81.2%' | To render |  | 0 | 0 | 0 | 0
2026-05-13 | Meta | Static Ad | Positioning | Ad 3: 'One pick · 9 sports' | To render |  | 0 | 0 | 0 | 0

## 3 · Ad Performance
AD PERFORMANCE — Meta + TikTok Spark, day-by-day
Date | Platform | Campaign | Ad / Creative | Spend | Impressions | Clicks | CPC | Conversions | CPL
2026-05-13 | Meta | LEAD-US-broad-20260513 | Ad: Receipts
2026-05-13 | Meta | LEAD-US-broad-20260513 | Ad: Lock
2026-05-13 | Meta | LEAD-US-broad-20260513 | Ad: Positioning

## 4 · Channel ROI
CHANNEL ROI — where are signups actually coming from?
Channel | $ Spent | Signups | CPL | % of total signups | Notes
Meta Ads
TikTok organic
TikTok Spark (paid boost)
X / Twitter organic
Instagram organic
Reddit
Influencer trades
ProductHunt
Founder essay
Email referrals (own list)
Direct / unknown

## 5 · Activations
VIRAL ACTIVATIONS — the 5 plays + status
# | Activation | Target launch | Status | Owner | Notes
1 | Position-jumping referral | Day 1 (live) | LIVE | Claude | Every signup gets pick1.live/?r=<code>. +100 positions per ref. 3 / 10 / 25 reward tiers.
2 | Public Accountability Bet | Day 8 (May 20) | Planned | Noa | 'If locks lose at < 60% over 30 days, first paid month refunded.' Needs public dashboard.
3 | Beat the AI challenge | Day 18 (May 30) | Planned | Claude (build) + Noa (launch) | Twitter hashtag #BeatPick1. Weekly leaderboard. Winner gets year of Pro.
4 | Influencer trade program | Day 4 (May 16) | Planned | Noa (DMs) + Claude (list) | DM 20 micro-influencers (5K-50K). Free year of Pro + custom ref code for honest 7-day review.
5 | Founder story drop | Day 14-15 (May 26-27) | Planned | Noa (record) + Claude (cross-post) | Coordinated multi-platform 'how I built this' content. Twitter thread + TikTok + IG + Substack.

## 6 · Influencer Outreach
INFLUENCER OUTREACH — 20-DM micro-trade program
Name / Handle | Platform | Followers | Niche | Status | DM sent date | Response | Posted? | Their ref code | Notes
(slot 1) |  |  |  | Cold
(slot 2) |  |  |  | Cold
(slot 3) |  |  |  | Cold
(slot 4) |  |  |  | Cold
(slot 5) |  |  |  | Cold
(slot 6) |  |  |  | Cold
(slot 7) |  |  |  | Cold
(slot 8) |  |  |  | Cold
(slot 9) |  |  |  | Cold
(slot 10) |  |  |  | Cold
(slot 11) |  |  |  | Cold
(slot 12) |  |  |  | Cold
(slot 13) |  |  |  | Cold
(slot 14) |  |  |  | Cold
(slot 15) |  |  |  | Cold
(slot 16) |  |  |  | Cold
(slot 17) |  |  |  | Cold
(slot 18) |  |  |  | Cold
(slot 19) |  |  |  | Cold
(slot 20) |  |  |  | Cold

## 7 · Pick Performance
PICK PERFORMANCE — daily record (the receipts wall)
Date | League | Game | Pick | Probability | Tier | Result | 1u P&L | Notes | Summary
2026-05-12 | NBA | SAS vs MIN G5 | San Antonio Spurs | 7860% | ** | WIN | +0.91 | Series 3-2 SAS | Total wins
2026-05-12 | NHL | VGK @ ANA G5 | Vegas Golden Knights | 5770% | * | WIN | +0.91 | Tied series winner | Total losses
2026-05-12 | NHL | MTL vs BUF G4 | Montreal Canadiens | 5610% | * | LOSS | -1.00 | Missed G4 | Win %
2026-05-13 | EPL | MCI vs CRY | Manchester City | 8120% | *** | Pending |  | Lock of the night | Lock (⭐⭐⭐) record
2026-05-13 | NHL | COL @ MIN G5 | Colorado Avalanche | 6360% | ** | Pending |  | Series closeout
2026-05-13 | NBA | DET vs CLE G5 | Detroit Pistons | 6060% | * | Pending |  | Tied series G5
2026-05-13 | NHL | MTL vs BUF G4 | Montreal Canadiens | 5610% | * | Pending |  | Carryover
2026-05-13 | NHL | VGK @ ANA G5 | Vegas Golden Knights | 5770% | * | Pending |  | Carryover